Experimental design and methods
Experiment summary
Compare the relative fitness of three rhizobia genotypes in the soil, plan-associated nonsymbiotic rhizosphere (vetch), symbiotic rhizosphere (clover), early symbiosis (3-week old clover nodules) and late symbiosis (6-week old clover nodules). This will be done in the presence (and absence?) of an artifical rhizobia community using three labelled strains of interest. Doing an experiment in the absence of the community too might help show how generalisable the results are when comparing different communities and also protect against potential low recovery of unlabelled strains from nodules if in a larger community the chosen strains are outcompeted.

Hypotheses:
Genotypes with high relative fitness during (late) symbiosis will be relatively less fit in the soil than other genotypes because of a trade-off between specialising in symbiotic competitiveness + efficiency and competitiveness in the soil. (this goes against the findings of an earlier study (Burghardt et al., 2018)⁠)

Genotypes that have high relative fitness in the nodule will also have higher relative fitness in the rhizosphere and early symbiosis. (this goes against findings of an earlier study (Zgadzaj et al., 2016)⁠)

Experimental design
Three-way marked strains only (3-weeks),
Three-way marked strains only (6-weeks),
= 12 clover replicates

Three-way marked strains only (5 weeks):
Soil microcosms: 6 replicates

Single strain inoculations for 3 marked strains,
= 3 * 6 clover replicates + 3 * 6 soil replicates

Uninoculated controls,
6 clover replicates

Different dilutions?

Totals:
24 soil microcosms, 36 clover microcosms

Notes:

Prepare rhizobia community
- Choose strains (3 marked strains and x unmarked strains)
- Prepare TY agar plates for each strain
- Pick strains from tubes in frozen strain library and streak onto prepared TY agar plates
- Incubate agar plates at 28C for 4 days
- Prepare glass tubes containing 6ml TY media
- Incubate glass tubes for 3 days at 28C
- Either mix equal volume (Burghardt et al., 2018)⁠, or measure ODs of equal volume for each strain, then adjust ODs prior to mixing equal volumes (Mendoza-Suárez et al., 2020)⁠.

Experiment timing
- Half of the replicates from each experiment are to be done in two batches (24 soil + 24 clover microcosms each set).
- This means on any one day, the most clover replicates that will need processing is 12.

Prepare sterile microcosms
- Fill and autoclave 96 microcosms with soil/sand.
- Can autoclave 12 at a time, which means 8 rounds. Autoclaving takes 2 hours.
- Pots are generally inoculated at planting, or sometimes pre-inoculated prior to planting. For our experiment, we to separate competitiveness in the soil from competitiveness for symbiosis, so minimising the effects of competition in the soil by inoculating either during planting or 2 weeks post planting (when the seed forms nodules) are most appropriate.

Inoculate microcosms
- Different studies use various inoculation sizes of artificial communities:
“At the time of planting, each pot was inoculated with 100 mL of the initial community (diluted in 0.85% NaCl solution to ∼10^6 bacteria per milliliter)” (Burghardt et al., 2018)⁠
“Inoculum was prepared by adding 1 mL of the Tagged-strain mix in 74 mL of 2.5× concentrated nitrogen-free rooting solution and then distributed homogenously into 500-mL pots.” (Mendoza-Suárez et al., 2020)⁠
“Plants were inoculated at sowing with 400 ml suspension of bacteria of interest (10^7 CFU/ml) grown in YEM broth.” (Boivin et al., 2020)⁠
- I will want to use the same set of clones for each inoculation, but don’t want them to evolve if my inoculations are staggered between sets of reps. I could cryopreserve clones in glycerol then re-incubate and re-mix my strain mix to the same final density and (equal) ratios. Or I could cryopreserve a sample from the first clone mixture, but the danger is the ratios of different strains change during the extended time in this mixture making it too different from before.

Process clover plants
- Photograph plants
- Cut off all nodules, count for each plant, and record number and weight.
- Sterilise outside of nodules then crush in TY solution.
- Plate dilutions of nodule solution (6-10 reps per plant) and incubate at 28C for 4 days.
- For 12 plants with 6 replicates, that’s 72 plates assuming say 6 serial dilutions fit on a single plate.
- Count colonies after 4 days
- Wash soil off that is attached to roots and vortex roots in solution. This is the “rhizosphere” sample.
- Again, plate rhizosphere isolates solution and count colonies after 4 days incubation.
- Dry out plants in oven for two days then weigh.

Process soil microcosms
- Vortex soil sample in solution, filter and plate. Count colonies as above.

Questions
- How long can I leave between autoclaving my microcosms and inoculating them?
- How can I stagger my inoculations without affecting the structure of my artificial community?
- Will differences in densities of bacteria released from nodules, rhizosphere and bulk soil and thus applied to colony-count plates affect (errors of) relative fitness measurements? How will this affect between-environment comparisons?

Boivin, S. et al. (2020) ‘Host-specific competitiveness to form nodules in Rhizobium leguminosarum symbiovar viciae’, New Phytologist, 226(2), pp. 555–568. doi: 10.1111/nph.16392.
Burghardt, L. T. et al. (2018) ‘Select and resequence reveals relative fitness of bacteria in symbiotic and free-living environments’, Proceedings of the National Academy of Sciences of the United States of America, 115(10), pp. 2425–2430. doi: 10.1073/pnas.1714246115.
Mendoza-Suárez, M. A. et al. (2020) ‘Optimizing Rhizobium-legume symbioses by simultaneous measurement of rhizobial competitiveness and N2 fixation in nodules’, Proceedings of the National Academy of Sciences of the United States of America, 117(18), pp. 9822–9831. doi: 10.1073/pnas.1921225117.
Zgadzaj, R. et al. (2016) ‘Root nodule symbiosis in Lotus japonicus drives the establishment of distinctive rhizosphere, root, and nodule bacterial communities’, Proceedings of the National Academy of Sciences of the United States of America, 113(49), pp. E7996–E8005. doi: 10.1073/pnas.1616564113.