Experimental evolution in soil
Experiment design summary
The rationale for the experiment is to explore the extent to which free-living rhizobia face trade-offs in evolving to compete better in the soil and in evolving traits for more effective symbiosis with legume hosts.

I will evolve two different labelled rhizobia strains separately in:
- soil microcosms
- soil microcosms with an added (static/not co-evolving) background community

These conditions will help me answer two main questions:
- To what extent does evolution in the soil alter symbiotic effectivness?
- To what extent does evolution to remain competitive in a microbial community also affect the evolution of symbiotic effectiveness?

After 10 weeks (10 transfers, how many generations?), I will have three populations: ancestral (A), evolved in soil (ES) and evolved in soil with background community (EC).

Each population will have six replicates. This means I will be evolving 12 replicate populations for each strain.

I will then compare the fitness of evolved clones to ancestral strains in the soil, and in the soil with the background community. I will also grow each replicate in a single-strain inoculation experiment with clover and measure the difference in symbiotic benefit to the plant by each strain. To summarise, for each strain:
A vs ES and A vs EC will be assayed in soil microcosms and soil + community microcosms, making a total of 24 competition experiments.
Additionally, there will be 18 single-strain inoculation experiments.

If I evolve two strains, that will be 24 microcosms to transfer each week. At the end of 10 weeks, there will be 48 competition experiments and 36 single-strain inoculations to carry out.

To summarise, for each strain:
- 6 ancestral replicates
- 6 replicates evolved alone in soil
- 6 replicates evolved with background community
- 10 weeks of weekly transfers to make evolved strains

Each transfer, the labelled strain is isolated from the soil microcosm and inoculated into a new microcosm. The background community is replaced each transfer using frozen stock.

At the end of the evolution phase, I will measure three things
1) Change in competitive fitness in the soil of ES and EC populations. I expect both populations to outcompete ancestors when grown in the soil in the absence of a community (if only the EC population performs better, this suggests evolving competitive interactions in the community is more beneficial or more evolutionarily accessible than traits for improved soil metabolism).
2) Change in competitive fitness in the soil+community of ES and EC populations. I expect EC to outcompete the ancestor, but ES to be less fit than the ancestor. This depends on the strength of selection for being a better competitor in the microbial community compared to growth in the soil. If “soil adaptations” are more important and “competitive adaptations” are negligibly important to success in the soil+community environment, then ES will outperform its ancestor. It also depends on the interaction (epistasis) between evolved “soil” versus “competitive” traits, if the interaction is positive, both EC and ES will outcompete ancestors, if evolving soil traits comes at an expense to competitive adaptations, ES will lose to its ancestor. To make that conclusion I would need to show that ES populations lose adaptations for competitive interactions faster than in most other environments (the effect of epistasis should be stronger than “neutral” loss of competitive traits which aren’t useful in the soil).
3) Single-strain symbiotic effectiveness. I can measure plant growth benefit (shoot dry weight) and number of nodules. I expect ES and EC populations to be less beneficial to the plant than ancestors. This assumes strains gradually lose adaptations for symbiotic effectiveness, or that traits that improve fitness in the soil come at a cost to symbiotic effectiveness. I will be able to detect evolutionary tradeoffs in nitrogen fixation effectiveness vs soil fitness, but not in in planta fitness vs soil fitness (unless I do competition assays in planta).

Experiment plan

Week 1
Prepare rhizobia background community
- Make streak plates for each strain in the community (say a 10-strain community).
- Grow two clones for each strain in glass TY microcosms.
- Cryopreserve individual clones (in case I need to re-make master mix tube)?
- Dilute one clone for each strain to the same OD and combine to make a “master” stock.
- Cryopreserve the master stock.

Preserving ancestral strains
- For the marked strain(s), make streak plates and isolate 6 clones. Perhaps split these clones into 2 separate tubes (three replicates for each clone) to ensure I have backups.
- Cryopreserve the 6 replicate clones + backups.
- These represent the ancestor and should be labelled with the opposite fluorescent marker to the evolving populations.
- In total I will have 12 cryopreserved ancestors (+ backups), 10 cryopreserved clones for the background community and one cryopreserved “mixed” background community.

Initial setup of soil microcosms
- After choosing the best soil from the preliminary experiment, fill 24 falcon tubes with 10g soil and autoclave these twice, one week apart.
- Inoculate soil microcosms with 100μl ancestral labelled strain + 100μl dH20. Inoculate soil+community microcosms with 100μl ancestral labelled strain + 100μl community crypreserved stock solution. I want the OD of the ancestral strain labelled strains to be high. How can I increase the density of the background community without incubation (which might change the ratio of different strains in the mix)? Should I re-make the background community each transfer from single cryopreserved clones to ensure they are present at equal densities each transfer?
- Put these tubes in the growth room(?) for 7 days.

Week 2 – week 13

For 8 transfers
- Prepare each set of 24 soil microcosms in advance
- Transfer each evolving strain by…
1) extracting soil wash
2) plating soil wash on gentamycin+TY agar for 3 days,
3) select labelled colonies and incubate in TY for 2 days,
4) inoculating prepared microcosms, half with background community added too.
5) incubate soil microcosms for 1 week.

If I do this, each growth + transfer period will take 12 days, which I estimate is enough for 8 transfers if I want to finish the labwork in 5 months. Plus, the strains will spend almost as much time growing in TY (and given more rapid growth rates, arguably more generations evolving in TY). To reduce the total time period I could reduce the growth period in soil to 5 days, but this makes the second problem worse (I have put thoughts on this at the end).

Week 14(? depending on no. transfers) - week 19

Competition assays
- I have two environments: soil and soil+community. There are twelve evolved replicates that need to be compared to their ancestor in each environment. That makes 24 competition assays.
- For each assay, I will grow cryopreserved ancestral and evolved strains for 1 day in TY medium, then measure their optical densities and dilute until they are approximately equal.
- I will then mix the ancestor and evolved strains in a 1:1 ratio by volume and grow for a further day together prior to plating.
- Before plating, I will do 3 dilutions for each treatment, making 24 * 3 = 72 agar plates to be prepared and spread.
- After 2-3 days I will count the number of colonies belonging to the ancestor and evolved strains, distinguished by their different fluorescent labels.

Make and inoculate clover microcosms
- Each strain has 6 ancestral replicates, 6 ES replicates and 6 EC replicates, making 18 total replicates.
- For two strains, that means 2 * 18 = 36 different clones to test in single strain inoculations.
- Is it necessary for me to measure measurement variation (i.e. grow multiple clovers with each clone)?
- Germinate clovers (4 days) and prepare sterile soil microcosms (1-week) for a total 40 microcosms (3-4 uninoculated controls).
- Incubate cryopreserved strains for 1-2 days and dilute to equal densities.
- Centrifuge to separate strains from TY, then replace TY with distilled water (to prevent growth on TY following addition to soil)?
- Grow clover for 3 or 6 weeks based on results of previous “genotype competition” experiment.

Measure clover growth
- Photograph plants
- Count nodules, remove and weigh as measures of symbiont fitness.
- Dry out plants in oven for 2 days, then measure shoot dry weight as an indirect measure of symbiont effectiveness.

Analysis
- For two strains, can calcualte the relative fitness of evolved and ancestral clones when grown in the soil, and in the soil with a background community. I will do this using the CFU counts from competition assays, which I will normalise by differences in growth rate between the ancestral and evolved strain in TY medium.
Example:
	CFU after plating in TY from soil wash	Doubling time in TY medium	Relative growth rate in TY medium	Adjusted CFU for differences in TY growth/”True” soil ratio.
Ancestral	10	4.8hrs	4.8/4.8 = 1	10 / 1 = 10
Evolved	20	3.6hrs	4.8/3.6 = 1.333	20 /1.333 = 15

Above, the original relative fitness measured by CFU counts is 2 (evolved/ancestral), and the adjusted relative fitness is 1.5.

My explanatory variables are
Environment: Soil / Soil+community
Evolution type: Ancestral / Evolved in soil / Evolved in soil with community
Strain: nodule-competitive / widespread genospecies.

My response variables are
Relative fitness (calculated from CFUs)
Shoot dry weight (grams)

Experimental design justification
- replacement of community each transfer makes it more likely we definitely recover our labelled strain, which might go extinct under co-evolution and allows selection to act in one direction which might be easier to interpret.

Questions
- How long do I need to incubate isolated labelled strains for between transfers? I need time to select labelled clones on agar and grow to a reasonable inoculation density in TY medium.

- If we make transfers to allow bacteria to continue to grow (and evolve) after reaching stationary phase in the original microcosm, should I test how long it takes for the number of CFUs isolated from the soil washes to stabilise? That way I could maximise the growth period between transfers if e.g. rhizobia are still growing after 7 days in the soil, I could extend the growth period. This would reduce the number of unnecessary transfers, limiting adaptation to TY media.

- If the “community” aspect is what prevents directly transferring soil washes from being viable, perhaps I could instead measure different soil types as my second treatment (as we have M3 and JI2), as opposed to presence/absence of background community, which might allow labelled strains to survive in high enough numbers to be transferred directly in the soil wash (no selection in transfer stage, so faster and doesn’t allow evolution in TY). I know this changes the experiment design quite a bit, but it depends how big the problem of the long transfer period is.

- Would it be useful for me to do another preliminary experiment growing some rhizobia in soil microcosms for 4 days, 7 days (with/without community) or 10 days and measuring their density to understand how frequently to transfer them (and how challenging it is after e.g. 1 transfer to extract a single labelled strain from a community of 10 strains)?

- How can I make sure that plating on TY agar for competition assays doesn’t bias my CFU counts of each strain because of differences in growth rates in TY medium between ancestral and evolved strains?