## Sheet1
Month	1					2					3					4					5
week	1	1	1	1	1	1	1	2	2	2	2	2	2	2	3	3	3	3	3	3	3	4	4	4	4	4	4	4	5	5	5	5	5	5	5	6	6	6	6	6	6	6	7	7	7	7	7	7	7	8	8	8	8	8	8	8	9	9	9	9	9	9	9	10	10	10	10	10	10	10	11	11	11	11	11	11	11	12	12	12	12	12	12	12	13	13	13	13	13	13	13	14	14	14	14	14	14	14	15	15	15	15	15	15	15	16	16	16	16	16	16	16	17	17	17	17	17	17	17	18	18	18	18	18	18	18	19	19	19	19	19	19	19	20	20	20	20	20	20	20	21	21	21	21	21	21	21	22	22	22
day	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63	64	65	66	67	68	69	70	71	72	73	74	75	76	77	78	79	80	81	82	83	84	85	86	87	88	89	90	91	92	93	94	95	96	97	98	99	100	101	102	103	104	105	106	107	108	109	110	111	112	113	114	115	116	117	118	119	120	121	122	123	124	125	126	127	128	129	130	131	132	133	134	135	136	137	138	139	140	141	142	143	144	145	146	147	148	149	150
Genotype Tradeoff experiment
Prepare microcosms
Germinate and plant clover
Inoculate microcosm set 1
Inoculate microcosm set 2
Plants are growing
Process 3-week old clovers (set 1) (isolate from nodules/rhizosphere, photo, dry)
Process 3-week old clovers (set 2)
Process 6-week old clovers (set 1)
Process 6-week old clovers (set 2)
Process soil microcosms (set 1)
Process soil microcosms (set 2)
Competition assays (make plates, make dilutions, incubate, analyse)
Measure plant dry weights

Evolution experiment
Set up microcosms
Prepare ancestral strains
Prepare background community
Growth
Transfer (isolate labelled strain, incubate, re-inoculate)
Competition assays (make plates, make dilutions, incubate, analyse)
Germinate and plant clover
Plants are growing
Take dry weight measurements of plants